Sample task list for fruit and vegetable bag scheme using local growers and a wholesaler

NB this document is an example for a particular type of food co-op but you can use this as a template to create your own volunteer task list and delete or adapt any sections that don’t apply.

| Tasks done by volunteers | Number | Time taken | Risks | Action |
| --- | --- | --- | --- | --- |
| - Taking orders including: - Recording the names of the people ordering. - Recording money collected for the others. - Storing money safely in cashbox. - Keeping tally of numbers of fruit and vegetable orders | 1-2 volunteers | 1 – 2 hours per day taking and checking orders. Possible phone calls on other days | Safe keeping of records Cashbox being taken | All order forms kept together in file The cashbox will be kept with an identified responsible person at all times when at centre The co-ordinator will take the cashbox home and store safely |
| - Phone local growers to place orders | 1 volunteer | 15 minutes | Volunteer being unwell or unable to contact grower | Another volunteer identified as stand in. Grower informed they should contact co-ordinator or stand if they are not contacted by the usual time |
| - Going to wholesaler to buy fruit - Taking all money collected for fruit orders from cashbox. - Using weekly price list and help of the wholesaler staff select what is the best quality fruit that day for our budget. - Making sure everyone gets at least 4 different kinds of fruit - Paying for fruit and keeping receipts for accounts. - Transporting the fruit to venue | At least 2 volunteers | 1 hour | Carrying large amount of cash Loss of receipts Lifting boxes that are too heavy | Two people to go to wholesaler whenever possible Records kept of weekly orders and wholesalers keeps copy of receipts. Volunteers will use food co-op trolleys and have lifting and handling training provided. Only trained volunteer will move produce. |
| - Calculating how many pieces of fruit each bag ordered has marking boxes | 1 volunteer | 15 minutes |  |  |
| - Sorting and counting out number of bags needed for - £1.25 fruit bags - £2.50 fruit bags - £1.25 vegetable bags - £2.50 vegetable bags | 1 volunteer | 5 minutes |  |  |
| - Filling fruit bags with number of fruit indicated on box | All volunteers | 15 - 30 minutes |  |  |
| - When vegetables delivered transferring any larger vegetable onto tables for sorting so growers can take back as many of their boxes as possible. | 2-3 volunteers | 5 minutes | Lifting too heavy weight | Volunteers have lifting and handling training. Work together to move boxes as necessary. |

| Tasks done by volunteers | Number | Time taken | Risks | Action |
| --- | --- | --- | --- | --- |
| - Counting and weighing out vegetables using electronic scales and putting into bags. | 2-3 volunteers 1 weighing, 1 putting into bags | 15 - 30 minutes | Vegetables can be dirty. | Gloves will be available for volunteers to use handling the vegetables, suggestion made to volunteers to wear older clothing or bring an apron. |
| - All fruit and vegetable bags are moved to the best point in the venue. | As many volunteers as possible | 5 minutes | Volunteers carrying too much | Volunteers will only carry a maximum of 2 bags each. |
| - Clear up any mess created to leave room as found - Throw away waste, boxes, compost mouldy fruit, etc. - Wipe down tables - Sweep up floor | As many volunteers as possible | 5 - 15 minutes | Waste unable to be disposed of safely on site and causes fire or health risk if left | A volunteer to agree to take away waste and dispose of this safely. |
| - Supervising collection of fruit and vegetables and adjusting records to know who’s collected or not. - Taking orders see task 1 | 1-2 volunteers | Done with task 1 | Someone taking produce that isn’t theirs | Volunteer always to be with the bags or an identified person made responsible. |
| - Delivering orders to - Older people on the estate by foot or car - Family centre - Taking orders see task 1 | 2-3 volunteers 1-2 volunteers | Would depend on where | Lifting and handling too much | Make use of trolley or car as necessary. |
| - Writing up and photocopying - Recipe, preparation or storage ideas for fruit and vegetables from members or other volunteers - Information on food co-op i.e. reminders to bring back bags, holiday weeks, request for feedback etc. | 1 volunteer Task can be shared | 15 - 30 minutes per week |  |  |
| - Attending 3-6 monthly meetings - Review the food co-op’s progress and check accounts. - Take notes of any action to be taken. | 3-4 volunteers 1 volunteer | 60 minutes |  |  |
|  | TOTAL | 5 hours 25 mins |  |  |